## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a system designer, I want to study IVR and conversational AI systems so that I can design the IVR simulator | MUST HAVE | Project documentation | System Designer | Completed
Sprint 2 | Sprint 2 | US002 | As a developer, I want to develop an integration layer for the existing IVR system so that it can communicate with the conversational platform | MUST HAVE | System architecture design | Backend Developer | Completed
Sprint 3 | Sprint 3 | US003 | As a user, I want the system to understand my input and process my request so that I can interact with the IVR system using natural language | MUST HAVE | Input Processing Module | AI Developer | Completed
Sprint 4 | Sprint 4 | US004 | As a user, I want a fully functional conversational IVR system so that I can complete tasks through voice interaction | MUST HAVE | System integration | Integration Developer | In Progress
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US001 | T1 | Study IVR architecture and conversational AI approaches | 2026-02-04 | 2026-02-06 | System Designer | Design | 3- Completed | 12 | bar: Day 1 to Day 6
US001 | T2 | Design IVR simulator architecture and workflow | 2026-02-07 | 2026-02-16 | System Designer | Design | 3- Completed | 11 | bar: Day 3 to Day 8
US002 | T3 | Develop integration layer for connecting IVR logic with conversational system | 2026-02-17 | 2026-03-02 | Backend Developer | Coding | 3- Completed | 11 | bar: Day 5 to Day 10
US003 | T4 | Implement module to process user input and generate responses | 2026-03-03 | 2026-03-16 | AI Developer | Coding | 3- Completed | 10 | bar: Day 7 to Day 12
US004 | T5 | Integrate conversational workflow and perform system validation | 2026-03-17 | 2026-03-30 | Integration Developer | Build | 2- In Progress | 10 | bar: Day 9 to Day 14
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 2 | Day 2 | Difficulty integrating legacy IVR flow with conversational processing | Analyzed call flow logic and created middleware interface
Sprint 2 | Day 4 | API response delay during voice request processing | Optimized request handling and reduced response time
Sprint 3 | Day 3 | Speech recognition accuracy issues with user voice input | Adjusted speech processing parameters and added validation
Sprint 4 | Day 1 | Frontend not receiving responses from backend service | Fixed API endpoint configuration and tested integration

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-04 | 2026-02-16 | System Designer | Document system architecture early | Starting development without full system understanding | Collaborative research and discussions | Created architecture documentation before development
2 | Sprint 2 | 2026-02-17 | 2026-03-02 | Backed Developer | Plan integration modules before coding | Making API changes without testing | Incremental development | Implemented integration layer successfully
3 | Sprint 3 | 2026-03-03 | 2026-03-16 | AI Developer | Improve input processing design upfront | Using unclear request handling logic | Iterative testing after each module | Optimized conversational logic and response accuracy
4 | Sprint 4 | 2026-03-17 | 2026-03-30 | Integration Developer | Perform integration testing earlier | Waiting until final stage to test | Cross-team coordination and communication | Conducted full system validation and resolved API issues