## Defect_tracker
SI No | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | 04/02/2026 | IVR call flow architecture diagram missing key module connections | Sprint 1 | System Designer | Documentation | Updated architecture diagram with complete IVR module connections | 05/02/2026 | Closed | Verified by team lead
2 | 08/02/2026 | IVR simulator workflow not matching original system design specifications | Sprint 1 | System Designer | Functional | Redesigned workflow to align with IVR system design document | 10/02/2026 | Closed | Design sign-off obtained
3 | 18/02/2026 | Legacy IVR flow integration failing due to incompatible middleware interface | Sprint 2 | Backend Developer | Integration | Analyzed legacy call flow logic and rebuilt middleware interface layer | 20/02/2026 | Closed | Integration tested successfully
4 | 22/02/2026 | API response delay exceeding 2 seconds during voice request processing | Sprint 2 | Backend Developer | Performance | Optimized async request handling and reduced unnecessary API calls | 23/02/2026 | Closed | Response time reduced to 1.3s
5 | 25/02/2026 | /ivr/tts/speak endpoint returning 500 error on empty text payload | Sprint 2 | Backend Developer | Functional | Added input validation and null check before TTS processing | 26/02/2026 | Closed | Verified via integration test TC002
6 | 04/03/2026 | Speech recognition accuracy dropping below threshold for multi-syllable inputs | Sprint 3 | AI Developer | Algorithmic | Adjusted speech processing parameters and added phonetic validation layer | 06/03/2026 | Closed | Accuracy restored above 95%
7 | 08/03/2026 | IVR collect-phone endpoint not handling non-numeric input gracefully | Sprint 3 | Backend Developer | Validation | Added regex validation and re-prompt logic for invalid phone inputs | 09/03/2026 | Closed | Verified via unit test TC006
8 | 12/03/2026 | Appointments menu returning duplicate time slots for same department | Sprint 3 | Backend Developer | Logic | Fixed slot deduplication logic in appointments query handler | 13/03/2026 | Closed | Verified via integration test TC007
9 | 18/03/2026 | Frontend not receiving responses from backend IVR service after deployment | Sprint 4 | Integration Developer | Integration | Fixed API endpoint configuration and updated CORS headers for frontend | 19/03/2026 | Closed | Full end-to-end test passed
10 | 22/03/2026 | Full booking flow failing at confirmation step due to missing session token | Sprint 4 | Integration Developer | Functional | Added session token persistence across IVR booking steps | 23/03/2026 | Closed | Verified via E2E test TC009
11 | 25/03/2026 | IVR start endpoint performance degrading under concurrent user load | Sprint 4 | Backend Developer | Performance | Implemented connection pooling and response caching for IVR start route | 26/03/2026 | Closed | Latency within threshold in TC010
12 | 27/03/2026 | TTS mocked unit test failing due to incorrect stub return type for audio bytes | Sprint 4 | Backend Developer | Unit Test | Corrected mock stub to return valid bytes object matching production TTS response format | 27/03/2026 | Open | Pending final review